## Bars
Title | Contained by | Team | Product/Initiatives | Description | Strategic Importance | Tags | Effort | Percent Complete | Start Date | End Date | Notes | Status | Comments
Centralized Freight Management (CFM) |  | ISCT | ISCT - Central Freight Management | Centralized Freight Mgmt tool manage all current freight rate, pickup allowance, line item freight, line item allowance, for our USBL locations. This system has bidirectional sync between USBL SUS and CFM tool itself. |  | ISCT |  | 87% | 2023-06-19 | 2024-02-20 |  | Planned
CFM Canada Fixes | Centralized Freight Management (CFM) | ISCT | ISCT - Central Freight Management |  |  |  |  | 86% | 2023-06-19 | 2024-02-20 |  | Planned
[CFM/FRDT]: FRDT US Enhancements | Centralized Freight Management (CFM) | ISCT | ISCT - Central Freight Management | CFM/FRDT Enhancement |  |  |  | 100% | 2023-06-19 | 2023-11-18 |  | Planned
Imports App | Centralized Freight Management (CFM) | ISCT | ISCT - Imports App/SID |  |  | ISCT |  | 68% | 2023-06-19 | 2023-11-18 |  | Planned
Corp.M Apps |  | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 92% | 2023-07-05 | 2024-03-07 |  | Planned
CMA - BAU FY24 Q2 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 80% | 2023-07-06 | 2024-02-10 |  | Planned
CMA Cloud Security - FY24 Q1 & FY24 Q2 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 85% | 2023-07-06 | 2024-02-10 |  | Planned
Corp Merch Platform | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2023-10-17 |  | Planned
Corp Merch Platform - MVP FY24 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 85% | 2023-07-06 | 2024-02-10 |  | Planned
IST - Release 1.1 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2024-02-11 |  | Planned
IST - Release 1.1.2 Stories | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2024-02-11 |  | Planned
IST - Release 1.3.0 Stories | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 36% | 2023-11-29 | 2024-01-31 |  | Planned
Local Flavor OKRA migration | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 55% | 2023-10-18 | 2024-02-11 |  | Planned
PGI Data Extract | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 37% | 2023-10-19 | 2024-02-10 |  | Planned
PGI Platform - Prod Support | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2023-10-18 |  | Planned
PGI Platform - Tech Debts - FY24 Q1 & FY24 Q2 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2024-02-09 |  | Planned
Supplier Fees - R 2.7.0 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 100% | 2023-07-06 | 2023-10-14 |  | Planned
Supplier Fees - Support Phase 2 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 82% | 2023-07-06 | 2024-02-11 |  | Planned
VBT- Support FY24 | Corp.M Apps | Corp. Merchandising | CM - Apps Platform |  |  | Corp.Merch |  | 68% | 2023-10-18 | 2024-02-05 |  | Planned
Corp.M PGM |  | Corp. Merchandising | CM - PGM |  |  | Corp.Merch |  | 82% | 2023-07-05 | 2024-03-07 |  | Planned
PGI - DB Performance | Corp.M PGM | Corp. Merchandising | CM - PGM |  |  | Corp.Merch |  | 97% | 2023-07-06 | 2024-02-05 |  | Planned
PGI - Phase 2 Enhancements | Corp.M PGM | Corp. Merchandising | CM - PGM |  |  | Corp.Merch |  | 73% | 2023-07-06 | 2024-02-06 |  | Planned
Corp.M Supplier Portal |  | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 55% | 2022-11-11 | 2024-03-07 |  | Planned
FY24 - Contact Management | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 60% | 2023-10-10 | 2024-02-13 |  | Planned
FY24 - Dashboard & Reporting | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  |  |  | 0% | 2023-07-10 | 2023-11-17 |  | Planned
FY24 - Enterprise Supplier View + SKU | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 0% | 2023-10-11 | 2024-02-13 |  | Planned
FY24 - Item Management | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  |  |  | 61% | 2023-07-10 | 2024-02-09 |  | Planned
FY24 - PAT | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 55% | 2023-07-09 | 2024-02-08 |  | Planned
FY24 - SSS as a Platform | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 60% | 2023-07-05 | 2024-02-09 |  | Planned
FY24 - Tech BAU | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 50% | 2023-07-09 | 2024-02-10 |  | Planned
FY24 - Vendor Broker Tie | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  |  | 2023-08-01 | 2023-10-02 |  | Planned
Sustainability - MVP2 - Data to SEED for Reporting | Corp.M Supplier Portal | Corp. Merchandising | CM - Supplier Portal |  |  | Corp.Merch |  | 26% | 2023-10-09 | 2024-02-13 |  | Planned
Engineering |  | ISCT | ISCT - BAU/Engineering |  |  | ISCT |  | 100% | 2023-07-01 | 2024-06-28 |  | Planned
AWS Cost Reduction Effort | Engineering | ISCT | ISCT - BAU/Engineering | Right-Sizing Resources: Analyze your usage patterns and adjust your AWS resources to match actual needs. This involves choosing the right instance types, storage options, and database configurations to avoid overprovisioning. Utilize Spot Instances: Take advantage of AWS Spot Instances for non-critical, fault-tolerant workloads. Spot Instances can provide significant cost savings compared to On-Demand or Reserved Instances. Reserved Instances: Consider purchasing AWS Reserved Instances for long-term stable workloads, as they offer cost savings over the pay-as-you-go On-Demand Instances. Optimize Storage: Use AWS data lifecycle policies to automatically move data to more cost-effective storage classes based on access patterns. Archiving infrequently accessed data to Glacier can result in considerable cost savings. |  |  |  | 100% | 2023-07-01 | 2024-06-28 |  | Planned
OKRA Migration | Engineering | ISCT | ISCT - BAU/Engineering |  |  | ISCT |  | 35% | 2023-11-10 | 2024-06-28 |  | Planned
GAH |  | GRAIN | GRAIN - GAH |  |  | GRAIN & ODI |  | 70% | 2023-07-01 | 2024-04-30 |  | Planned
Application Maintenance (BAU) | GAH | GRAIN | GRAIN - GAH |  |  | GRAIN & ODI |  | 83% | 2023-07-01 | 2024-03-31 |  | Planned
Enhancement Requests (BAU) | GAH | GRAIN | GRAIN - GAH |  |  | GRAIN & ODI |  | 47% | 2023-07-01 | 2024-03-31 |  | Planned
New Requests (BAU) | GAH | GRAIN | GRAIN - GAH |  |  | GRAIN & ODI |  | 81% | 2023-07-01 | 2024-03-31 |  | Planned
Support (BAU) | GAH | GRAIN | GRAIN - GAH |  |  | GRAIN & ODI |  | 76% | 2023-07-01 | 2024-03-31 |  | Planned
OBTE - Performance Culture |  | OBT-Engineering | OBTE - Performance Culture |  |  | OBTE |  | 91% | 2023-07-05 | 2024-02-18 |  | Planned
FY23_Stop Attribute | OBTE - Performance Culture | OBT-Engineering | OBTE - Performance Culture |  |  |  |  | 91% | 2023-07-07 | 2024-01-29 |  | Planned
OBTE - Tech Initiatives |  | OBT-Engineering |  |  |  | OBTE |  | 89% | 2023-07-31 | 2024-03-14 |  | Planned
eRoad/Cortex | OBTE - Tech Initiatives | OBT-Engineering |  |  |  | OBTE |  | 91% | 2023-08-02 | 2024-03-14 |  | Planned
FY23 ARI Modernization | OBTE - Tech Initiatives | OBT-Engineering | [5 empty] | 90% | 2023-08-02 | 2024-03-13 |  | Planned
FY23 ARI Support | OBTE - Tech Initiatives | OBT-Engineering | [5 empty] | 86% | 2023-08-02 | 2024-03-13 |  | Planned
FY23_Fetch BY data to Roadnet | OBTE - Tech Initiatives | OBT-Engineering | [5 empty] | 93% | 2023-08-02 | 2023-10-19 |  | Planned
FY23_OREO/ARI Pre Routing | OBTE - Tech Initiatives | OBT-Engineering | [5 empty] | 95% | 2023-08-02 | 2024-03-12 |  | Planned
FY24_Cyber Vulnerability | OBTE - Tech Initiatives | OBT-Engineering |  |  |  | OBTE |  | 81% | 2023-08-02 | 2024-03-08 |  | Planned
FY24_OMNI/ARI Integration | OBTE - Tech Initiatives | OBT-Engineering |  |  |  | OBTE |  | 69% | 2023-08-02 | 2024-03-10 |  | Planned
ODI |  | GRAIN | GRAIN - ODI |  |  | GRAIN & ODI |  | 89% | 2023-07-01 | 2024-04-30 |  | Planned
OREO - OMNI |  | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 95% | 2023-07-01 | 2024-02-27 |  | Planned
FY23_OREO/ARI Pre Routing | OREO - OMNI | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 95% | 2023-07-04 | 2024-02-26 |  | Planned
FY23 Post OMNI 1.0 : BOS | OREO - OMNI | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 100% | 2023-07-04 | 2023-11-23 |  | Planned
FY23 Post OMNI 1.0 : Common Items | OREO - OMNI | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 100% | 2023-07-04 | 2024-01-19 |  | Planned
FY23 Post OMNI 1.0 : E2E Testing | OREO - OMNI | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 96% | 2023-07-04 | 2024-02-26 |  | Planned
OREO Omni 1.0 Hypercare | OREO - OMNI | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 92% | 2023-07-04 | 2024-02-25 |  | Planned
OREO - Tech Initiatives |  | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 89% | 2023-07-01 | 2024-02-29 |  | Planned
FY23 ASOH Intl.Ecom | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 92% | 2023-07-04 | 2024-02-26 |  | Planned
FY23 OREO Management Console | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  |  |  | 94% | 2023-10-21 | 2024-02-25 |  | Planned
FY23 OREO Support | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 88% | 2023-07-04 | 2024-02-26 |  | Planned
FY23 Vault Integration | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 92% | 2023-07-04 | 2024-02-27 |  | Planned
FY24 Cyber Security | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 60% | 2023-07-04 | 2024-02-29 |  | Planned
FY24 Disaster Recovery | OREO - Tech Initiatives | CDS | CDS - Enterprise Omni Channel |  |  | OREO |  | 95% | 2023-07-04 | 2024-02-25 |  | Planned
SOLAR |  | GRAIN | GRAIN - SOLAR |  |  | GRAIN & ODI |  | 46% | 2023-07-12 | 2024-04-30 |  | Planned
SWMS Cloud Acceleration |  | SWMS | SWMS - Cloud Acceleration |  |  | SWMS, SWMS Cloud Acceleration |  | 100% | 2023-07-05 | 2023-10-28 |  | Planned
SWMS Ireland Cloud Migration | SWMS Cloud Acceleration | SWMS | SWMS - Cloud Acceleration |  |  | SWMS, SWMS Cloud Acceleration |  | 100% | 2023-07-10 | 2023-10-21 |  | Planned
SWMS Java Migration POC |  | SWMS | SWMS - Java Migration |  |  | SWMS, SWMS Java Migration |  | 44% | 2023-11-05 | 2024-12-01 |  | Planned
Multi-Tenant RF host service | SWMS Java Migration POC | SWMS | SWMS - Java Migration |  |  | SWMS, SWMS Java Migration |  | 54% | 2023-11-08 | 2024-03-19 |  | Planned
New (Java) Live Receiving | SWMS Java Migration POC | SWMS | SWMS - Java Migration |  |  | SWMS, SWMS Java Migration |  | 28% | 2024-01-01 | 2024-09-30 |  | Planned
SWMS Mobile Modernization |  | SWMS | SWMS - Mobile Apps Modernization |  |  | SWMS, SWMS Mobile |  | 87% | 2023-03-01 | 2024-03-31 |  | Planned
Android 11 Migration | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration was deprioritised due to Ireland English feature. |  | SWMS, SWMS Mobile |  | 80% | 2023-10-01 | 2024-03-01 |  | Planned
HTTP to HTTPS Migration | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization |  |  | SWMS, SWMS Mobile |  | 100% | 2023-03-01 | 2023-11-18 |  | Planned
Ireland English | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization | Ireland/ English Feature - Localization |  | SWMS, SWMS Mobile |  | 100% | 2023-10-18 | 2023-11-17 |  | Planned
MSKU | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization |  |  | SWMS, SWMS Mobile |  | 97% | 2023-12-01 | 2024-01-31 |  | Planned
R55 | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization | Compatible Mobile Version for R55 SLS,SOS and RF |  | SWMS, SWMS Mobile |  | 100% | 2023-04-03 | 2023-07-31 |  | Planned
R56/R57 | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization | New urgency has been created for R57 to get into production.This is mainly in order to reduce CPP |  | SWMS, SWMS Mobile |  | 100% | 2023-12-01 | 2024-01-29 |  | Planned
R58/59 | SWMS Mobile Modernization | SWMS | SWMS - Mobile Apps Modernization |  |  | SWMS, SWMS Mobile |  | 0% | 2024-02-01 | 2024-03-31 |  | Planned
SWMS New UI General Availability |  | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 97% | 2023-01-23 | 2025-03-31 |  | Planned
Full Order CrossDock Version V57 Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-05-15 | 2024-05-29 |  | Planned
Greco CrossDock Version V575 Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-05-15 | 2024-05-29 |  | Planned
SWMS New UI - Blue Yonder feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) | Currently no changes for new UI as of R55 |  | SWMS, SWMS New UI |  | 100% | 2023-07-01 | 2023-10-21 |  | Planned
SWMS New UI - Blue Yonder Version V55 Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2023-09-20 | 2023-10-21 |  | Planned
SWMS New UI - Bug Fixes Version V55 Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2023-08-14 | 2023-10-21 |  | Planned
SWMS New UI - Labor Module Current Batch Stabilisation | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2023-03-28 | 2023-08-26 |  | Planned
SWMS New UI - Miniload Feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 6% | 2024-03-04 | 2024-05-14 |  | Planned
SWMS New UI - New UI Version Parity beyond V58 | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-03-13 | 2024-12-31 |  | Planned
SWMS New UI - Outside Storage Feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-05-15 | 2024-07-16 |  | Planned
SWMS New UI Prod Rollout Support | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-03-31 | 2024-12-31 |  | Planned
SWMS New UI - RDC integration Feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 97% | 2023-08-29 | 2024-01-31 |  | Planned
SWMS New UI - V58 Feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-02-29 | 2024-04-30 |  | Planned
V55.0.02 to V57.1 Feature Parity | SWMS New UI General Availability | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 57% | 2024-01-02 | 2025-03-31 |  | Planned
SWMS New UI QE Improvements |  | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  |  | 2023-10-01 | 2024-04-27 |  | Planned
[QE][Automation] RDC Functional Test Automation | SWMS New UI QE Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 42% | 2024-01-24 | 2024-02-28 |  | Planned
Regression failure fixing after P3/P4 issues merged.. | SWMS New UI QE Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 92% | 2023-10-01 | 2024-02-29 |  | Planned
SWMS New UI Tech Debts and Architectural Improvements |  | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2023-02-01 | 2024-06-19 |  | Planned
2.0 Tech Foundations | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2023-08-13 | 2023-12-19 |  | Planned
Implement a mechanism to autorefresh (or ask the user to refresh) the frontend if there is a newer version | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2023-04-01 | 2024-02-02 |  | Planned
[New UI][ARCHITECTURAL_ENHANCEMENT] Multi Tenant Deployment Support for New UI BFF | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 0% | 2024-02-06 | 2024-03-31 |  | Planned
[New UI][ARCHITECTURAL_ENHANCEMENT] Multi Tenant Deployment Support for New UI FE Layer | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 50% | 2024-01-24 | 2024-02-20 |  | Planned
[New UI][Tech Debt] Enable continuous delivery | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 50% | 2023-02-21 | 2024-03-31 |  | Planned
[New UI][Tech Debt] Move New UI Artifacts from JFrog to Github Packages | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2024-01-10 | 2024-01-23 |  | Planned
[New UI][Tech Debt] Test Framework Enhancements | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 100% | 2023-02-01 | 2024-01-23 |  | Planned
[SWMS][NEW UI][ARCHITECTURAL_ENHANCEMENT]Setup Optimizely for Feature Flagging in New UI components | SWMS New UI Tech Debts and Architectural Improvements | SWMS | SWMS - UI Modernization (New UI) |  |  | SWMS, SWMS New UI |  | 50% | 2024-01-24 | 2024-02-20 |  | Planned
SWMS RDC Cloud Migration |  | SWMS | SWMS - RDC Cloud Migration |  |  | SWMS, SWMS RDC Cloud Migration |  | 86% | 2023-07-23 | 2024-08-24 |  | Planned
SWMS RDC Cloud Migration -Development | SWMS RDC Cloud Migration | SWMS | SWMS - RDC Cloud Migration |  |  | SWMS RDC Cloud Migration |  | 85% | 2023-07-23 | 2024-04-24 |  | Planned
SWMS RDC Cloud Migration - UAT | SWMS RDC Cloud Migration | SWMS | SWMS - RDC Cloud Migration |  |  | SWMS RDC Cloud Migration |  |  | 2024-04-25 | 2024-06-15 |  | Planned
Sysco Inventory Management 360 (SIM360) |  | ISCT | ISCT - SIM360 - IA | Sysco Inventory Management 360 (SIM360) is the modern cloud-native inventory management suite of products with capabilities like Inventory 360 Visibility (IA), Service Level Insights (SLI), SMS purchase order management, SMS produce truck build application (Dispatch Sheet), Corporate Billing As a Service etc. SIM360 is integrated with our systems of record for Inbound Supply Chain like SUS, RME, DPR, TMS, CFM, FRDT etc. |  | ISCT |  | 87% | 2022-06-16 | 2024-06-28 |  | Planned
IA Refactoring | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - CIS |  |  | ISCT |  | 85% | 2023-06-05 | 2024-03-14 |  | Planned
Inbound Scheduling | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - CIS | Agree on requirements and solution design. |  |  |  | 100% | 2023-02-15 | 2023-05-31 |  | Planned
Inbound Scheduling ¦ Dock Door Scheduling | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - Door Dock Appoitment Scheduling |  |  | ISCT |  | 80% | 2023-09-03 | 2024-02-28 |  | Planned
Inbound Supply Chain Integration Links -SIM 360 (Innovation) | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - Innovation |  |  | ISCT |  | 100% | 2023-06-09 | 2023-11-23 |  | Planned
MSR Integration | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - MSR Integration | Developing an API to fetch the Buyer ID, Advisor ID, and Next Projected PO Delivery date for all the valid items of given site/sites. API should support both USBL and RDC sites. |  | ISCT |  | 77% | 2023-12-27 | 2024-02-15 |  | Planned
Mule Modernization | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - Mule Modernization |  |  | ISCT |  | 0% | 2024-02-07 | 2024-06-28 |  | Planned
OMNI 1.0 Integration Support | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - OMNI |  |  | ISCT |  | 92% | 2023-12-01 | 2024-01-19 |  | Planned
PO ¦ House Confirmation (Paragon) | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - PO |  |  | ISCT |  | 96% | 2023-06-01 | 2024-02-15 |  | Planned
PO ¦ Vendor confirmation (EDI855) | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 Vendor Confirmation | Prod release for first vendors to support EDI855 and Hypercare support. |  | ISCT |  | 95% | 2023-06-01 | 2024-03-04 |  | Planned
RDC Truckfill App in SIM360 | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - RDC Truckfill for SIM360 |  |  | ISCT |  |  | 2024-01-22 | 2024-03-23 |  | Planned
Service Level Insights: Fill-in PO & Customer Specific Info | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - SLI |  |  | ISCT |  | 96% | 2023-06-01 | 2024-03-14 |  | Planned
Service Level Insights ¦ User Feedback Improvements | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - SLI | Incorporating changes and improvements suggested by users of Service Level Insights. |  | ISCT |  | 30% | 2023-12-02 | 2024-06-14 |  | Planned
SIM360 Conversational AI & NLP Project - MVP1 (Innovation) | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - Innovation |  |  |  |  | 64% | 2023-06-03 | 2024-03-14 |  | Planned
SIM360 Pulse | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 Pulse |  |  | ISCT |  |  | 2024-01-18 | 2024-03-19 |  | Planned
Vendor Cost Maintenance Modernization | Sysco Inventory Management 360 (SIM360) | ISCT | ISCT - SIM360 - Vendor Cost Maintenance Modernization | Objective is to modernize 3 RME screens and build them on SIM360 platform. - OT4T: OpCo, Ship point, Price point maintenance - CT2I: Price inquiry by item - CT2J: Price inquiry by vendor |  | ISCT |  | 50% | 2023-06-08 | 2024-03-14 |  | Planned
Tableau |  | GRAIN | GRAIN - Tableau (USBL) |  |  | GRAIN & ODI |  | 95% | 2023-07-01 | 2024-04-30 |  | Planned
Event Chargeback | Tableau | GRAIN | GRAIN - Tableau (USBL) |  |  | GRAIN & ODI |  | 90% | 2024-01-15 | 2024-02-09 |  | Planned
Rebate Report | Tableau | GRAIN | GRAIN - Tableau (USBL) |  |  | GRAIN & ODI |  | 100% | 2024-01-30 | 2024-02-07 |  | Planned
VeraCode Integration |  | ISCT | ISCT - BAU/Engineering |  |  | ISCT |  | 30% | 2023-11-01 | 2024-03-29 |  | Planned
Vision |  | GRAIN | GRAIN - Vision |  |  | GRAIN & ODI |  | 68% | 2023-07-01 | 2024-04-30 |  | Planned
Application Maintenance (BAU) | Vision | GRAIN | GRAIN - Vision |  |  | GRAIN & ODI |  | 45% | 2023-07-01 | 2024-03-31 |  | Planned
Enhancement Requests (BAU) | Vision | GRAIN | GRAIN - Vision |  |  | GRAIN & ODI |  | 75% | 2023-07-01 | 2024-03-31 |  | Planned
New Requests (BAU) | Vision | GRAIN | GRAIN - Vision |  |  | GRAIN & ODI |  | 77% | 2023-07-01 | 2024-03-31 |  | Planned
Warehouse Live |  | GRAIN | GRAIN - Warehouse Live |  |  | GRAIN & ODI |  | 74% | 2023-07-01 | 2024-04-30 |  | Planned

## Milestones
Team | Product/Initiatives | Milestone | Milestone Description | Deadline | Title
SWMS | SWMS - UI Modernization (New UI) | Central warehouse Feature Parity |  | 2024-06-05
SWMS | SWMS - UI Modernization (New UI) | Miniload Feature Parity |  | 2024-03-31
SWMS | SWMS - UI Modernization (New UI) | V56 & V57 version Parity |  | 2024-02-29
SWMS | SWMS - Mobile Apps Modernization | MSKU |  | 2024-01-29
SWMS | SWMS - Mobile Apps Modernization | Omni Feature Parity and V 55 GA |  | 2024-11-30
SWMS | SWMS - UI Modernization (New UI) | Container Files Feature Parity |  | 2024-07-08
SWMS | SWMS - UI Modernization (New UI) | R1 and Grecko Feature Parity |  | 2024-11-02
SWMS | SWMS - UI Modernization (New UI) | DOD Feature Parity |  | 2024-09-22
SWMS | SWMS - UI Modernization (New UI) | Asian Foods |  | 2024-08-13
SWMS | SWMS - UI Modernization (New UI) | Outside Storage |  | 2024-05-09
SWMS | SWMS - Cloud Acceleration | SWMS AWS Rollouts USBL and Canada | 258 Regina 259 Winnipeg 180 Toronto 274 Thunder Bay 045 Los Angeles 064 St. Louis 101 Ventura 162 Kelowna | 2023-08-05
SWMS | SWMS - Cloud Acceleration | 073- Hamptdon Road AWS Migration | 073 - Hamptons Road | 2023-12-09
SWMS | SWMS - Cloud Acceleration | SWMS Ireland OpCo 564 AWS Migration | 564 Cork | 2023-09-16
SWMS | SWMS - UI Modernization (New UI) | SWMS Labor Module Current Batch Stabilisation Prod Release |  | 2023-08-26
SWMS | SWMS - UI Modernization (New UI) | SWMS Classic 040 Idaho Cutover | SWMS Classic 040 Idaho Cutover | 2023-10-07
SWMS | SWMS - Cloud Acceleration | SWMS AWS Rollouts USBL & Canada | 139 Victoria 265 Halifax 331 Boucherville 067 Houston | 2023-08-12
SWMS | SWMS - Mobile Apps Modernization | HTTPS pilot to Intermountain | HTTPS on (only)RF went pilot to 005(Intermountain).This was done in only RF device. | 2023-12-05
SWMS | SWMS - Mobile Apps Modernization | R56/R57 | QE Certified and UAT Certified by January 27. | 2024-01-29
SWMS | SWMS - Java Migration | Enable new (Java) Live Receiving for multiple sites. | No code changes. Enable the feature flag for 2 or more sites. | 2024-09-30
SWMS | SWMS - Cloud Acceleration | SWMS Ireland Cloud Migration 349,499,303 | 349 Dublin 499 Lisburn 303 - Newcastle West | 2023-10-14
SWMS | SWMS - Cloud Acceleration | SWMS GB OpCo 901 , 194 AWS Migration | 901 - Harlow 194 - Central Illionis | 2023-10-21
SWMS | SWMS - UI Modernization (New UI) | SWMS V55 & Blueyonder Feature parity Prod Release |  | 2023-10-21
SWMS | SWMS - UI Modernization (New UI) | SWMS New UI RDC Integration feature parity Development Completion |  | 2024-01-20
SWMS | SWMS - Java Migration | Enable new (Java) Live Receving for multiple sites | All sites use the new Java based Live Receiving. | 2024-09-30
SWMS | SWMS - Java Migration | Multi-Tenant RF host service for one site | RF Host service will be deployed in AWS ECS with multi-tenancy support. One site will start to use above. Multi-Tenancy and ECS support are part of the code base. | 2024-04-30
SWMS |  | Enable HTTPS | Enable End to end encryption request response, QE Competed and UAT pending | 2023-10-30
SWMS | SWMS - Java Migration | Onboard R58 sites to the RF Host service | This will cover all US broadline and Canada | 2024-07-31
SWMS | SWMS - Java Migration | Onboard all US broadline and Canada with the same version (57.1) to the RF Host service (GA) |  | 2024-06-30
SWMS | SWMS - Java Migration | Onboard two or more sites (Same version, 57.1) to Multi-Tenant RF host service | No code changes More sites will be wired with the ECS hosted service | 2024-05-31
SWMS | SWMS - Java Migration | Enable new (Java) Live Receiving for a beta site. | Converted live receiving code is fully functional, tested and deployed. RF BFF code to support new (Java) flow will be deployed. | 2024-08-31
SWMS | SWMS - Cloud Acceleration | All Ireland OpCos SWMS V55 Upgrade | 564 Cork 349 Dublin 499 Lisburn | 2023-10-28
SWMS | SWMS - Java Migration | Make new (Java) Live Receiving GA | All sites use the new Java based LR | 2024-12-01
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration 2nd Pilot & Go Live | 177- Northeast RDC | 2024-08-24
SWMS | SWMS - RDC Cloud Migration | SWMS RDC AWS Migration Development Completion | Both DEV & QE | 2024-04-24
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration 1st Pilot- 184 Southeast RDC | 184 Southeast RDC | 2024-07-25
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration UAT Completion |  | 2024-06-15
SWMS | SWMS - Mobile Apps Modernization | Android R55 Parity in production |  | 2023-08-19
SWMS | SWMS - Mobile Apps Modernization | Ireland English - SOS | Ireland English - SOS feature will be delivered on the 14th November 2023. | 2023-11-15
SWMS | SWMS - Mobile Apps Modernization | Ireland English | Ireland English - RF feature will be delivered on the 13th November 2023. | 2023-11-13
SWMS | SWMS - Mobile Apps Modernization | Ireland English - SLS | Ireland English - SLS feature will be delivered on the 17th November 2023. | 2023-11-17
SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration | Migration of SWMS Mobile RF, SOS, and SLS applications from Android 10 to Android 11. | 2024-03-01
SWMS | SWMS - UI Modernization (New UI) | SWMS New UI - Arkansas Pilot |  | 2023-11-12
SWMS | SWMS - Mobile Apps Modernization | HTTP to HTTPS Migration | Build SWMS Mobile Applications (SOS/SLS/RF) to be accessible and functional over HTTPS. HTTPS(only) Release was on the Nov 18th. | 2023-11-18
SWMS | SWMS - Mobile Apps Modernization | Ireland Production Go Live | Ireland (RF,SOS,SLS) Production with HTTPS enabled Go Live on the Dec 12th | 2023-12-12
ISCT | ISCT - SIM360 - IA | IA Refactoring Prod | IA v1.0.0.0 | 2024-02-29
ISCT | ISCT - SIM360 - Vendor Cost Maintenance Modernization | OT4T/CT2I/CT2J QA Release | Purchasing MDM v1.0.0.0 | 2024-02-16
ISCT | ISCT - SIM360 - MSR Integration | MSR Integration |  | 2024-02-21
ISCT | ISCT - SIM360 - SLI | SLI ¦ User Feedback | v1.3.0.12 | 2024-01-31
ISCT | ISCT - OMNI | OMNI 1.0.0.8 | Update in next projected PO batch criteria | 2024-02-02
ISCT | ISCT - Central Freight Management | FRDT Enhancements | Freight Rates Database Tool | 2023-08-05
ISCT | ISCT - SIM360 - CIS | CIS Initial Release | Centralised Inbound Scheduling | 2023-08-22
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R10 | Service Level Insights | 2023-10-31
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R7 |  | 2023-08-25
ISCT | ISCT - SIM360 Vendor Confirmation | PO ¦ Vendor Confirmation Prod |  | 2024-02-03
ISCT | ISCT - SIM360 - CIS | CIS - TMS Minor Release | Centralised Inbound Scheduling. Transport Management System | 2023-10-19
ISCT | ISCT - Central Freight Management | FRDT Fixes | Freight Rates Database Tool | 2023-09-19
ISCT | ISCT - Imports App/SID | Imports App Security Fixes (Tentative) | Imports App is for Bahamas | 2023-11-27
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R11 | Service Level Insights | 2023-12-04
ISCT | ISCT - Central Freight Management | CFM - Security Fixes | Centralized Freight Management | 2023-11-14
ISCT | ISCT - Central Freight Management | CFM - Canada Fixes | Centralized Freight Management | 2023-10-16
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R8 | Service Level Insights | 2023-09-26
ISCT | ISCT - SIM360 - CIS | CIS - TMS - PO Interface | Centralised Inbound Scheduling - Appointment Interface - Once TMS creates an Appointment pass that to SUS boxes. | 2023-09-15
ISCT | ISCT - OMNI | OMNI 1.0.0.4 | SUS to DOM Sales Order Creation, Supply & Order Event interface kinesis to kafka migration | 2023-09-06
ISCT | ISCT - SIM360 - PO | MERCH 1.5.0.45 | Apply Aurora I/O Optimized cluster mode to the production merchandising and integrated planning RDS clusters | 2023-09-06
ISCT | ISCT - SIM360 - PO | MERCH 1.5.0.47 | External link integration for SIM360 (CFM, FRDT and Imports App) | 2023-09-25
ISCT | ISCT - SIM360 - Door Dock Appoitment Scheduling | Dock Door Scheduling QA |  | 2024-02-16
ISCT | ISCT - SIM360 - CIS | CIS - TMS Fixes | Centralised Inbound Scheduling. Transport Management System | 2023-10-10
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release | Release 1.196.0v - VBT Commodity Flag | 2023-10-23
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.184.0v - PAT Refresh Anchor Point-Follower (LAP only) | 2023-09-06
Corp. Merchandising | CM - Apps Platform | VBT 2.1.0 |  | 2024-02-19
Corp. Merchandising | CM - PGI (Apps Team) | PGI 1.9.1 (Tentative) |  | 2024-02-22
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.167.0v - Blue Dot Revamp Rejection Logic (MVP 02) , Test Plan ¦ SDP -1.167.0v Release 1.175.0v - FnB "Deny" to "Rejected" , Test Plan ¦ SDP -1.175.0v Release 1.178.0v – PAT Override revised-pricing-lot with GAP Release 1.180.0v - Autoslotting - New Items Not getting pick up Release 1.181.0v - COO Banner | 2023-08-14
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release | Release 1.196.0v - VBT Commodity Flag ¦Test Plan ¦ VBT -1.196.0v | 2023-11-06
Corp. Merchandising | CM - Paper Lotting | Paper Lot CRs |  | 2023-12-01
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.8.1 |  | 2023-12-04
Corp. Merchandising | CM - Customer Decision Trees | CDT - 1.2.1 | Customer Decision Tress | 2023-12-04
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.8.0 | Big fixes and improvements | 2023-11-21
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.173.0v - Contact Management - PGI Role Enhancements | 2023-09-26
Corp. Merchandising | CM - IST Devolopment | IST 1.3.0 (Tentative) |  | 2024-02-12
Corp. Merchandising | ISCT - BAU/Engineering | Supplier Data Portal Release (Tentative) |  | 2024-02-05
Corp. Merchandising | CM - Customer Decision Trees | CDT - 1.2.0 | Customer Decision Trees | 2023-11-13
Corp. Merchandising | ISCT - Central Freight Management | Supplier Data Portal Minor Release | Release 1.141.0v - Item API JAVA 17 Update Release 1.174.0v - CN removal flag should pass to NetMenu directly (MVP 01) Release 1.204.0v - GAP Values not flowing down to LAP (Partially Released – SALES_LOAD schedule change only) | 2023-11-13
Corp. Merchandising | CM - IST Devolopment | IST 1.1.2 | Item Selection Tool | 2023-12-05
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release |  | 2023-11-20
Corp. Merchandising | CM - Customer Decision Trees | CDT 1.1.0 | Customer Decision Trees | 2023-09-26
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.189.0v - Fix multiple primary contacts | 2023-10-02
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.152.0v – Tech BAU Fargate Migration MVP 01 (Profiling API) | 2023-10-09
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Release | Release 1.207.0v – F&B Auto Approval (Turn on AA Process) https://syscobt.atlassian.net/wiki/spaces/MDMSUPPLIER/pages/4131127488/Release+1.207.0v+-+F+B+Auto+Approval+Turn+on+AA+Process | 2024-01-08
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.9.0 (Tentative) |  | 2024-01-30
Corp. Merchandising | CM - PGI (Apps Team) | PGI DB Migration Prod Deployment |  | 2023-11-09
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.6.7 |  | 2023-07-31
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.186.0v – PAT Global LPG Logic change (without report) ¦Test Plan ¦ PAT -1.186.0v Release 1.195.0v - Patch Feedback hide for non-supplier visible items No high/critical issues reported. | 2023-10-16
Corp. Merchandising | CM - IST Devolopment | IST 1.1.0 | Item Selection Tool | 2023-08-09
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.3 |  | 2023-09-26
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.0 |  | 2023-08-24
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.1 |  | 2023-09-06
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.2 |  | 2023-09-12
Corp. Merchandising | CM - IST Devolopment | IST 1.1.1 | Item Selection Tool | 2023-10-03
OBT-Engineering | OBTE - Cortex | Cortex Pilot | East Texas (293) | 2023-07-29
OBT-Engineering | OBTE - Cortex | Cortex (08 OpCos) |  | 2023-11-04
OBT-Engineering | OBTE - Cortex | Cortex (2 OpCos) | 001-Jackson and 078-West Texas | 2023-08-26
OBT-Engineering | OBTE - Cortex | Cortex (3 OpCos) |  | 2023-09-09
OBT-Engineering | OBTE - Cortex | Cortex (10 OpCos) |  | 2023-11-11
OBT-Engineering | OBTE - BAU | Service Time Override (21 OpCos) |  | 2023-11-03
OBT-Engineering | OBTE - BAU | Service Time Override Changes | Delivery service time. Customer specific. Only updated customers will get updated to RoadNet | 2024-01-16
OBT-Engineering | OBTE - Cortex | Cortex (08OpCos) |  | 2024-01-13
OBT-Engineering | OBTE - Cortex | Cortex (14 OpCo) |  | 2024-01-27
OBT-Engineering | OBTE - Cortex | Cortex (3 OpCos) |  | 2023-10-01
OBT-Engineering | OBTE - ARI Modernization | ODI Changes to RN |  | 2023-09-22
OBT-Engineering | OBTE - Cortex | Cortex (6 OpCos) |  | 2023-10-08
OBT-Engineering | OBTE - Cortex | Cortex (09 OpCos) |  | 2023-10-21
OBT-Engineering | OBTE - Performance Culture | Stop Attribute MVP 1 (Tentative) |  | 2024-02-19
OBT-Engineering | OBTE - ARI Modernization | Pre Routing Go Live |  | 2023-08-07
OBT-Engineering | OBTE - BAU | Service Time Override (10 OpCos) | ODI service time send to Roadnet | 2023-10-21
OBT-Engineering | OBTE - Cortex | Cortex (09 OpCos) |  | 2023-10-28
OBT-Engineering |  | FY24 OMNI - April Release |  | 2024-04-27
OBT-Engineering | OBTE - ARI Modernization | Pre Routing Go Live |  | 2023-08-07
CDS | CDS - Enterprise Omni Channel | OMNI Dec 09 Release |  | 2023-12-09
CDS | CDS - Tech Initiatives | ASOH Streaming and Bulk Service |  | 2023-08-22
CDS | CDS - Enterprise Omni Channel | FY24 - OMNI Sep 29 Release | Bulk Order Subscription (BOS 2.0) | 2023-10-10
CDS | CDS - Enterprise Omni Channel | FY24 OMNI - June Release | Hub & Spoke | 2024-06-15
CDS | CDS - Enterprise Omni Channel | OMNI January Release |  | 2024-02-03
CDS | CDS - Enterprise Omni Channel | OMNI Oct 17th Releasse |  | 2023-10-20
CDS | CDS - Enterprise Omni Channel | OMNI 31st Oct Release | Bug fixes | 2023-11-11
CDS | CDS - Tech Initiatives | DR (Order Status Service) |  | 2024-01-28
GRAIN | GRAIN - GAH | GAH - Backend Revamp | Python 3.8 to 3.11 | 2024-04-30
GRAIN | GRAIN - Tableau (USBL) | Total Team Selling Dashboard Go-live |  | 2023-08-08
GRAIN | GRAIN - GAH | GAH - Frontend Revamp | Angular 5 to 17 | 2024-03-29
GRAIN | GRAIN - SOLAR | SOLAR - Onboarding Allan Town OpCo |  | 2024-04-30
GRAIN | GRAIN - Vision | Vision - Frontend Revamp |  | 2024-04-30
GRAIN | GRAIN - Tableau (USBL) | Tableau - Rebate Report Go-live |  | 2024-02-16
GRAIN | GRAIN - Tableau (USBL) | CX KPI Dashboard Go-live |  | 2023-08-25
GRAIN | GRAIN - Tableau (USBL) | Tableau - Event Chargeback Go-live |  | 2024-02-16
GRAIN | GRAIN - Tableau (USBL) | CX KPI Dashboard Go-live |  | 2024-01-11
GRAIN | GRAIN - Tableau (USBL) | US Ops Dashboard Go-live |  | 2023-09-27
GRAIN | GRAIN - Tableau (USBL) | Fuel Surcharge Dashboard Go-live |  | 2023-11-22
GRAIN | GRAIN - Tableau (USBL) | TTS Dashboard Go-live |  | 2023-10-13
GRAIN | GRAIN - Warehouse Live | WHL - Cache database integration |  | 2023-10-05
GRAIN | GRAIN - Tableau (USBL) | Total team Selling Dashboard Go-live |  | 2024-01-11
GRAIN | GRAIN - Warehouse Live | WHL - Onboarding RDC OpCos |  | 2024-02-16

## Releases
Team | Initiative | Bar Name | Start Date | End Date
SWMS | SWMS - Mobile Apps Modernization | SWMS Mobile Modernization | 2023-03-01 | 2024-03-31
SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration | 2023-10-01 | 2024-03-01
SWMS | SWMS - Mobile Apps Modernization | HTTP to HTTPS Migration | 2023-03-01 | 2023-11-18
SWMS | SWMS - Mobile Apps Modernization | Ireland English | 2023-10-18 | 2023-11-17
SWMS | SWMS - Mobile Apps Modernization | MSKU | 2023-12-01 | 2024-01-31
SWMS | SWMS - Mobile Apps Modernization | R55 | 2023-04-03 | 2023-07-31
SWMS | SWMS - Mobile Apps Modernization | R56/R57 | 2023-12-01 | 2024-01-29
SWMS | SWMS - Mobile Apps Modernization | R58/59 | 2024-02-01 | 2024-03-31

## Field Data
Product/Initiative | Team
CDS - BAU | CDS
CDS - Enterprise Omni Channel | CDS
CDS - Tech Initiatives | CDS
CM - Apps Platform | Corp. Merchandising
CM - BAU/Engineering | Corp. Merchandising
CM - Customer Decision Trees | Corp. Merchandising
CM - IST Devolopment | Corp. Merchandising
CM - MDM Platform | Corp. Merchandising
CM - Paper Lotting | Corp. Merchandising
CM - PGI (Apps Team) | Corp. Merchandising
CM - PGM | Corp. Merchandising
CM - Supplier Fee | Corp. Merchandising
CM - Supplier Portal | Corp. Merchandising
GRAIN - Vision | GRAIN
GRAIN - SOLAR | GRAIN
GRAIN - GAH | GRAIN
GRAIN - Warehouse Live | GRAIN
GRAIN - Tableau (USBL) | GRAIN
GRAIN - ODI | GRAIN
OBTE - ARI Modernization | OBT-Engineering
OBTE - BAU | OBT-Engineering
OBTE - Cortex | OBT-Engineering
OBTE - Performance Culture | OBT-Engineering
SWMS - Blue Yonder (LMS) | SWMS
SWMS - Brakes | SWMS
SWMS - Chick-Fil-A | SWMS
SWMS - Cloud Acceleration | SWMS
SWMS - Cloud Agnostic | SWMS
SWMS - CMU Full Order Cross-Dock | SWMS
SWMS - Data Science | SWMS
SWMS - Delivery Sleeve | SWMS
SWMS - Enterprise Omni Channel | SWMS
SWMS - Infrastructure Upgrades (Oracle 19C) | SWMS
SWMS - Integrations Modernization | SWMS
SWMS - International | SWMS
SWMS - Mobile Apps Modernization | SWMS
SWMS - Modernization ProC to PL/SQL | SWMS
SWMS - OPCO | SWMS
SWMS - Platform | SWMS
SWMS - Platform DBA | SWMS
SWMS - Quinyx (LPS) | SWMS
SWMS - RDC | SWMS
SWMS - RDC Cloud Migration | SWMS
SWMS - Release Automation | SWMS
SWMS - SCM R&D | SWMS
SWMS - STS | SWMS
SWMS - SWAP | SWMS
SWMS - Test Automation & Stability | SWMS
SWMS - UI Modernization (New UI) | SWMS
SWMS - Warehouse Moves | SWMS
SWMS - Java Migration | SWMS
ISCT - BAU/Engineering | ISCT
ISCT - Central Freight Management | ISCT
ISCT - CFM/FRDT US Enhancements | ISCT
ISCT - DPR | ISCT
ISCT - DPR/SUS IMS & Merch Modernization | ISCT
ISCT - Global Inventory Management | ISCT
ISCT - Global Inventory Management (House Confirmation) | ISCT
ISCT - IA Enhancements | ISCT
ISCT - Imports App/SID | ISCT
ISCT - Integrated Planning | ISCT
ISCT - Item and Vendor API | ISCT
ISCT - Item Mainteance | ISCT
ISCT - OMNI | ISCT
ISCT - OMNI (IM Platform Dev & SUS to DOM Interface) | ISCT
ISCT - PO Management System | ISCT
ISCT - RME Platform Upgrade POC | ISCT
ISCT - SCM R&D | ISCT
ISCT - Service Level Insights | ISCT
ISCT - SIM360 - CIS | ISCT
ISCT - SIM360 - DFIO | ISCT
ISCT - SIM360 - Dock Door Appointment Scheduling | ISCT
ISCT - SIM360 - IA | ISCT
ISCT - SIM360 - Innovation | ISCT
ISCT - SIM360 - MSR Integration | ISCT
ISCT - SIM360 - Mule Modernization | ISCT
ISCT - SIM360 - PO | ISCT
ISCT - SIM360 - SLI | ISCT
ISCT - SIM360 - Vendor Cost Maintenance Modernization | ISCT
ISCT - SIM360 Vendor Confirmation | ISCT
ISCT - SIM360 - RDC Truckfill for SIM360 | ISCT
ISCT - SIM360 Pulse | ISCT