## Bars
Release_ID | Team | Initiative | Release_Name | Start_Date | End_Date
1 | SWMS | SWMS - UI Modernization (New UI) | [New UI][Tech Debt] Move New UI Artifacts from JFrog to Github Packages | 2024-01-10 | 2024-01-23
2 | SWMS | SWMS - UI Modernization (New UI) | SWMS New UI RDC Integration feature parity Development Completion | 2024-01-10 | 2024-01-23
3 | SWMS | SWMS - UI Modernization (New UI) | [New UI][Tech Debt] Test Framework Enhancements | 2023-02-01 | 2024-01-23
4 | SWMS | SWMS - UI Modernization (New UI) | [New UI][ARCHITECTURAL_ENHANCEMENT] Multi Tenant Deployment Support for New UI FE Layer | 2024-01-24 | 2024-02-20
5 | SWMS | SWMS - UI Modernization (New UI) | [SWMS][NEW UI][ARCHITECTURAL_ENHANCEMENT]Setup Optimizely for Feature Flagging in New UI components | 2024-01-24 | 2024-02-20
6 | SWMS | SWMS - UI Modernization (New UI) | Implement a mechanism to autorefresh (or ask the user to refresh) the frontend if there is a newer version | 2023-04-01 | 2023-02-02
7 | SWMS | SWMS - UI Modernization (New UI) | [New UI][Tech Debt] Enable continuous delivery | 2023-02-21 | 2024-03-31
8 | SWMS | SWMS - UI Modernization (New UI) | [New UI][ARCHITECTURAL_ENHANCEMENT] Multi Tenant Deployment Support for New UI BFF | 2024-02-06 | 2024-03-31
9 | SWMS | SWMS - UI Modernization (New UI) | Regression failure fixing after P3/P4 issues merged | 2023-10-01 | 2024-02-29
10 | SWMS | SWMS - UI Modernization (New UI) | [QE][Automation] RDC Functional Test Automation | 2024-01-24 | 2024-02-28
11 | SWMS | SWMS - Mobile Apps Modernization | HTTP to HTTPS Migration | 2023-03-01 | 2023-11-18
12 | SWMS | SWMS - Mobile Apps Modernization | Compatible Mobile Version for R55 SLS,SOS and RF | 2023-04-03 | 2023-07-31
13 | SWMS | SWMS - Mobile Apps Modernization | MSKU | 2023-12-01 | 2024-03-09
14 | SWMS | SWMS - Mobile Apps Modernization | Ireland/ English Feature - Localization | 2023-10-18 | 2023-11-17
15 | SWMS | SWMS - Mobile Apps Modernization | R56/R57 | 2023-12-01 | 2024-01-29
16 | SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration | 2023-10-01 | 2024-03-01
17 | SWMS | SWMS - Mobile Apps Modernization | R58/59 | 2024-02-01 | 2024-03-31
18 | SWMS | SWMS - Java Migration | Multi-Tenant RF host service | 2023-11-08 | 2024-03-19
19 | SWMS | SWMS - Java Migration | New (Java) Live Receiving | 2024-01-01 | 2024-09-30
20 | SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration -Development | 2023-07-23 | 2024-04-24
21 | SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration - UAT | 2024-04-25 | 2024-06-15
22 | ISCT | ISCT - Central Freight Management | Centralized Freight Management (CFM) | 06/19/2023 | 02/20/2024
23 | ISCT | ISCT - Central Freight Management | CFM Canada Fixes | 06/19/2023 | 02/20/2024
24 | ISCT | ISCT - Central Freight Management | [CFM/FRDT]: FRDT US Enhancements | 06/19/2023 | 11/18/2023
25 | ISCT | ISCT - Imports App/SID | Imports App | 06/19/2023 | 11/18/2023
26 | ISCT | ISCT - BAU/Engineering | Engineering | 07/01/2023 | 06/28/2024
27 | ISCT | ISCT - BAU/Engineering | AWS Cost Reduction Effort | 07/01/2023 | 06/28/2024
28 | ISCT | ISCT - BAU/Engineering | OKRA Migration | 11/10/2023 | 06/28/2024
29 | ISCT | ISCT - SIM360 - IA | Sysco Inventory Management 360 (SIM360) | 06/16/2022 | 06/28/2024
30 | ISCT | ISCT - SIM360 - CIS | IA Refactoring | 06/05/2023 | 03/14/2024
31 | ISCT | ISCT - SIM360 - CIS | Inbound Scheduling | 02/15/2023 | 05/31/2023
32 | ISCT | ISCT - SIM360 - Door Dock Appoitment Scheduling | Inbound Scheduling ¦ Dock Door Scheduling | 09/03/2023 | 02/28/2024
33 | ISCT | ISCT - SIM360 - Innovation | Inbound Supply Chain Integration Links -SIM 360 (Innovation) | 06/09/2023 | 11/23/2023
34 | ISCT | ISCT - SIM360 - MSR Integration | MSR Integration | 12/27/2023 | 02/15/2024
35 | ISCT |  | Mule Modernization | 02/07/2024 | 06/28/2024
36 | ISCT | ISCT - OMNI | OMNI 1.0 Integration Support | 12/01/2023 | 01/19/2024
37 | ISCT |  | PO ¦ House Confirmation (Paragon) | 06/01/2023 | 02/15/2024
38 | ISCT | ISCT - SIM360 Vendor Confirmation | PO ¦ Vendor confirmation (EDI855) | 06/01/2023 | 03/04/2024
39 | ISCT |  | RDC Truckfill App in SIM360 | 01/22/2024 | 03/23/2024
40 | ISCT | ISCT - SIM360 - SLI | Service Level Insights: Fill-in PO & Customer Specific Info | 06/01/2023 | 03/14/2024
41 | ISCT | ISCT - SIM360 - SLI | Service Level Insights ¦ User Feedback Improvements | 12/02/2023 | 06/14/2024
42 | ISCT | ISCT - SIM360 - Innovation | SIM360 Conversational AI & NLP Project - MVP1 (Innovation) | 06/03/2023 | 03/14/2024
43 | ISCT |  | SIM360 Pulse | 01/18/2024 | 03/19/2024
44 | ISCT | ISCT - SIM360 - Vendor Cost Maintenance Modernization | Vendor Cost Maintenance Modernization | 06/08/2023 | 03/14/2024
45 | ISCT | ISCT - BAU/Engineering | VeraCode Integration | 11/01/2023 | 03/29/2024
46 | Corp. Merchandising | CM - Apps Platform | CMA - BAU FY24 Q2 | 07/05/2023 | 03/07/2024
47 | Corp. Merchandising | CM - Apps Platform | CMA Cloud Security - FY24 Q1 & FY24 Q2 | 07/06/2023 | 02/10/2024
48 | Corp. Merchandising | CM - Apps Platform | Corp Merch Platform | 07/06/2023 | 02/10/2024
49 | Corp. Merchandising | CM - Apps Platform | Corp Merch Platform - MVP FY24 | 07/06/2023 | 10/17/2023
50 | Corp. Merchandising | CM - Apps Platform | IST - Release 1.1 | 07/06/2023 | 02/10/2024
51 | Corp. Merchandising | CM - Apps Platform | IST - Release 1.1.2 Stories | 07/06/2023 | 02/11/2024
52 | Corp. Merchandising | CM - Apps Platform | IST - Release 1.3.0 Stories | 07/06/2023 | 02/11/2024
53 | Corp. Merchandising | CM - Apps Platform | Local Flavor OKRA migration | 11/29/2023 | 01/31/2024
54 | Corp. Merchandising | CM - Apps Platform | PGI Data Extract | 10/18/2023 | 02/11/2024
55 | Corp. Merchandising | CM - Apps Platform | PGI Platform - Prod Support | 10/19/2023 | 02/10/2024
56 | Corp. Merchandising | CM - Apps Platform | PGI Platform - Tech Debts - FY24 Q1 & FY24 Q2 | 07/06/2023 | 10/18/2023
57 | Corp. Merchandising | CM - Apps Platform | Supplier Fees - R 2.7.0 | 07/06/2023 | 02/09/2024
58 | Corp. Merchandising | CM - Apps Platform | Supplier Fees - Support Phase 2 | 07/06/2023 | 10/14/2023
59 | Corp. Merchandising | CM - Apps Platform | VBT- Support FY24 | 07/06/2023 | 02/11/2024
60 | Corp. Merchandising | CM - PGM | PGI - DB Performance | 10/18/2023 | 02/05/2024
61 | Corp. Merchandising | CM - PGM | PGI - Phase 2 Enhancements | 07/06/2023 | 02/06/2024
62 | Corp. Merchandising | CM - Supplier Portal | FY24 - Contact Management | 10/10/2023 | 02/13/2024
63 | Corp. Merchandising | CM - Supplier Portal | FY24 - Dashboard & Reporting | 07/10/2023 | 11/17/2023
64 | Corp. Merchandising | CM - Supplier Portal | FY24 - Enterprise Supplier View + SKU | 10/11/2023 | 02/13/2024
65 | Corp. Merchandising | CM - Supplier Portal | FY24 - Item Management | 07/10/2023 | 02/09/2024
66 | Corp. Merchandising | CM - Supplier Portal | FY24 - PAT | 07/09/2023 | 02/08/2024
67 | Corp. Merchandising | CM - Supplier Portal | FY24 - SSS as a Platform | 07/05/2023 | 02/09/2024
68 | Corp. Merchandising | CM - Supplier Portal | FY24 - Tech BAU | 07/09/2023 | 02/10/2024
69 | Corp. Merchandising | CM - Supplier Portal | FY24 - Vendor Broker Tie | 08/01/2023 | 10/02/2023
70 | Corp. Merchandising | CM - Supplier Portal | Sustainability - MVP2 - Data to SEED for Reporting | 10/09/2023 | 02/13/2024
71 | OBT-Engineering | OBTE - Performance Culture | FY23_Stop Attribute | 07/07/2023 | 01/29/2024
72 | OBT-Engineering | OBTE - Cortex | eRoad/Cortex | 08/02/2023 | 03/14/2024
73 | OBT-Engineering | OBTE - ARI Modernization | FY23 ARI Modernization | 08/02/2023 | 03/13/2024
74 | OBT-Engineering | OBTE - ARI Modernization | FY23 ARI Support | 08/02/2023 | 03/13/2024
75 | OBT-Engineering | OBTE - ARI Modernization | FY23_Fetch BY data to Roadnet | 08/02/2023 | 10/19/2023
76 | OBT-Engineering | OBTE - ARI Modernization | FY23_OREO/ARI Pre Routing | 08/02/2023 | 03/12/2024
77 | OBT-Engineering | OBTE - ARI Modernization | FY24_Cyber Vulnerability | 08/02/2023 | 03/08/2024
78 | OBT-Engineering | OBTE - ARI Modernization | FY24_OMNI/ARI Integration | 08/02/2023 | 03/10/2024
79 | OREO | OREO - Enterprise Omni Channel | FY23_OREO/ARI Pre Routing | 07/04/2023 | 02/26/2024
80 | OREO | OREO - Enterprise Omni Channel | FY23 Post OMNI 1.0 : BOS | 07/04/2023 | 11/23/2023
81 | OREO | OREO - Enterprise Omni Channel | FY23 Post OMNI 1.0 : Common Items | 07/04/2023 | 01/19/2024
82 | OREO | OREO - Enterprise Omni Channel | FY23 Post OMNI 1.0 : E2E Testing | 07/04/2023 | 02/26/2024
83 | OREO | OREO - Enterprise Omni Channel | OREO Omni 1.0 Hypercare | 07/04/2023 | 02/25/2024
84 | OREO | OREO - Tech Initiatives | FY23 ASOH Intl.Ecom | 07/04/2023 | 02/26/2024
85 | OREO | OREO - Tech Initiatives | FY23 OREO Management Console | 10/21/2023 | 02/25/2024
86 | OREO | OREO - Tech Initiatives | FY23 OREO Support | 07/04/2023 | 02/26/2024
87 | OREO | OREO - Tech Initiatives | FY23 Vault Integration | 07/04/2023 | 02/27/2024
88 | OREO | OREO - Tech Initiatives | FY24 Cyber Security | 07/04/2023 | 02/29/2024
89 | OREO | OREO - Tech Initiatives | FY24 Disaster Recovery | 07/04/2023 | 02/25/2024
90 | GRAIN | GRAIN - Vision | Application Maintenance (BAU) | 07/01/2023 | 03/31/2024
91 | GRAIN | GRAIN - Vision | Enhancement Requests (BAU) | 07/01/2023 | 03/31/2024
92 | GRAIN | GRAIN - Vision | New Requests (BAU) | 07/01/2023 | 03/31/2024
93 | GRAIN | GRAIN - SOLAR | SOLAR | 07/12/2023 | 04/30/2024
94 | GRAIN | GRAIN - Warehouse Live | Warehouse Live | 07/01/2023 | 04/30/2024
95 | GRAIN | GRAIN - ODI | ODI | 07/01/2023 | 04/30/2024
96 | GRAIN | GRAIN - Tableau (USBL) | Event Chargeback | 15-01-2024 | 12-02-2024
97 | GRAIN | GRAIN - Tableau (USBL) | Rebate Report | 30-01-2024 | 13-02-2024
98 | SWMS | SWMS - Mobile Apps Modernization | R57.1 | 01-12-2023 | 16-03-2023
99 | ISCT | ISCT - SIM360 - RDC Truckfill for SIM360 | Purchasing MDM(OT4T/CT21/CT2J) | 08-06-2023 | 14-03-2024

## Milestones
Team | Product/Initiatives | Milestone | Milestone Description | Deadline | Title
SWMS | SWMS - UI Modernization (New UI) | Central warehouse Feature Parity |  | 2024-06-05
SWMS | SWMS - UI Modernization (New UI) | Miniload Feature Parity |  | 2024-03-31
SWMS | SWMS - UI Modernization (New UI) | V56 & V57 version Parity |  | 2024-02-29
SWMS | SWMS - Mobile Apps Modernization | MSKU |  | 2024-01-29
SWMS | SWMS - Mobile Apps Modernization | Omni Feature Parity and V 55 GA |  | 2024-11-30
SWMS | SWMS - UI Modernization (New UI) | Container Files Feature Parity |  | 2024-07-08
SWMS | SWMS - UI Modernization (New UI) | R1 and Grecko Feature Parity |  | 2024-11-02
SWMS | SWMS - UI Modernization (New UI) | DOD Feature Parity |  | 2024-09-22
SWMS | SWMS - UI Modernization (New UI) | Asian Foods |  | 2024-08-13
SWMS | SWMS - UI Modernization (New UI) | Outside Storage |  | 2024-05-09
SWMS | SWMS - Cloud Acceleration | SWMS AWS Rollouts USBL and Canada | 258 Regina 259 Winnipeg 180 Toronto 274 Thunder Bay 045 Los Angeles 064 St. Louis 101 Ventura 162 Kelowna | 2023-08-05
SWMS | SWMS - Cloud Acceleration | 073- Hamptdon Road AWS Migration | 073 - Hamptons Road | 2023-12-09
SWMS | SWMS - Cloud Acceleration | SWMS Ireland OpCo 564 AWS Migration | 564 Cork | 2023-09-16
SWMS | SWMS - UI Modernization (New UI) | SWMS Labor Module Current Batch Stabilisation Prod Release |  | 2023-08-26
SWMS | SWMS - UI Modernization (New UI) | SWMS Classic 040 Idaho Cutover | SWMS Classic 040 Idaho Cutover | 2023-10-07
SWMS | SWMS - Cloud Acceleration | SWMS AWS Rollouts USBL & Canada | 139 Victoria 265 Halifax 331 Boucherville 067 Houston | 2023-08-12
SWMS | SWMS - Mobile Apps Modernization | HTTPS pilot to Intermountain | HTTPS on (only)RF went pilot to 005(Intermountain).This was done in only RF device. | 2023-12-05
SWMS | SWMS - Mobile Apps Modernization | R56/R57 | QE Certified and UAT Certified by January 27. | 2024-01-29
SWMS | SWMS - Java Migration | Enable new (Java) Live Receiving for multiple sites. | No code changes. Enable the feature flag for 2 or more sites. | 2024-09-30
SWMS | SWMS - Cloud Acceleration | SWMS Ireland Cloud Migration 349,499,303 | 349 Dublin 499 Lisburn 303 - Newcastle West | 2023-10-14
SWMS | SWMS - Cloud Acceleration | SWMS GB OpCo 901 , 194 AWS Migration | 901 - Harlow 194 - Central Illionis | 2023-10-21
SWMS | SWMS - UI Modernization (New UI) | SWMS V55 & Blueyonder Feature parity Prod Release |  | 2023-10-21
SWMS | SWMS - UI Modernization (New UI) | SWMS New UI RDC Integration feature parity Development Completion |  | 2024-01-20
SWMS | SWMS - Java Migration | Enable new (Java) Live Receving for multiple sites | All sites use the new Java based Live Receiving. | 2024-09-30
SWMS | SWMS - Java Migration | Multi-Tenant RF host service for one site | RF Host service will be deployed in AWS ECS with multi-tenancy support. One site will start to use above. Multi-Tenancy and ECS support are part of the code base. | 2024-04-30
SWMS |  | Enable HTTPS | Enable End to end encryption request response, QE Competed and UAT pending | 2023-10-30
SWMS | SWMS - Java Migration | Onboard R58 sites to the RF Host service | This will cover all US broadline and Canada | 2024-07-31
SWMS | SWMS - Java Migration | Onboard all US broadline and Canada with the same version (57.1) to the RF Host service (GA) |  | 2024-06-30
SWMS | SWMS - Java Migration | Onboard two or more sites (Same version, 57.1) to Multi-Tenant RF host service | No code changes More sites will be wired with the ECS hosted service | 2024-05-31
SWMS | SWMS - Java Migration | Enable new (Java) Live Receiving for a beta site. | Converted live receiving code is fully functional, tested and deployed. RF BFF code to support new (Java) flow will be deployed. | 2024-08-31
SWMS | SWMS - Cloud Acceleration | All Ireland OpCos SWMS V55 Upgrade | 564 Cork 349 Dublin 499 Lisburn | 2023-10-28
SWMS | SWMS - Java Migration | Make new (Java) Live Receiving GA | All sites use the new Java based LR | 2024-12-01
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration 2nd Pilot & Go Live | 177- Northeast RDC | 2024-08-24
SWMS | SWMS - RDC Cloud Migration | SWMS RDC AWS Migration Development Completion | Both DEV & QE | 2024-04-24
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration 1st Pilot- 184 Southeast RDC | 184 Southeast RDC | 2024-07-25
SWMS | SWMS - RDC Cloud Migration | SWMS RDC Cloud Migration UAT Completion |  | 2024-06-15
SWMS | SWMS - Mobile Apps Modernization | Android R55 Parity in production |  | 2023-08-19
SWMS | SWMS - Mobile Apps Modernization | Ireland English - SOS | Ireland English - SOS feature will be delivered on the 14th November 2023. | 2023-11-15
SWMS | SWMS - Mobile Apps Modernization | Ireland English | Ireland English - RF feature will be delivered on the 13th November 2023. | 2023-11-13
SWMS | SWMS - Mobile Apps Modernization | Ireland English - SLS | Ireland English - SLS feature will be delivered on the 17th November 2023. | 2023-11-17
SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration | Migration of SWMS Mobile RF, SOS, and SLS applications from Android 10 to Android 11. | 2024-03-01
SWMS | SWMS - UI Modernization (New UI) | SWMS New UI - Arkansas Pilot |  | 2023-11-12
SWMS | SWMS - Mobile Apps Modernization | HTTP to HTTPS Migration | Build SWMS Mobile Applications (SOS/SLS/RF) to be accessible and functional over HTTPS. HTTPS(only) Release was on the Nov 18th. | 2023-11-18
SWMS | SWMS - Mobile Apps Modernization | Ireland Production Go Live | Ireland (RF,SOS,SLS) Production with HTTPS enabled Go Live on the Dec 12th | 2023-12-12
ISCT | ISCT - SIM360 - IA | IA Refactoring Prod | IA v1.0.0.0 | 2024-02-29
ISCT | ISCT - SIM360 - Vendor Cost Maintenance Modernization | OT4T/CT2I/CT2J QA Release | Purchasing MDM v1.0.0.0 | 2024-02-16
ISCT | ISCT - SIM360 - MSR Integration | MSR Integration |  | 2024-02-21
ISCT | ISCT - SIM360 - SLI | SLI ¦ User Feedback | v1.3.0.12 | 2024-01-31
ISCT | ISCT - OMNI | OMNI 1.0.0.8 | Update in next projected PO batch criteria | 2024-02-02
ISCT | ISCT - Central Freight Management | FRDT Enhancements | Freight Rates Database Tool | 2023-08-05
ISCT | ISCT - SIM360 - CIS | CIS Initial Release | Centralised Inbound Scheduling | 2023-08-22
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R10 | Service Level Insights | 2023-10-31
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R7 |  | 2023-08-25
ISCT | ISCT - SIM360 Vendor Confirmation | PO ¦ Vendor Confirmation Prod |  | 2024-02-03
ISCT | ISCT - SIM360 - CIS | CIS - TMS Minor Release | Centralised Inbound Scheduling. Transport Management System | 2023-10-19
ISCT | ISCT - Central Freight Management | FRDT Fixes | Freight Rates Database Tool | 2023-09-19
ISCT | ISCT - Imports App/SID | Imports App Security Fixes (Tentative) | Imports App is for Bahamas | 2023-11-27
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R11 | Service Level Insights | 2023-12-04
ISCT | ISCT - Central Freight Management | CFM - Security Fixes | Centralized Freight Management | 2023-11-14
ISCT | ISCT - Central Freight Management | CFM - Canada Fixes | Centralized Freight Management | 2023-10-16
ISCT | ISCT - SIM360 - SLI | SLI Post MVP R8 | Service Level Insights | 2023-09-26
ISCT | ISCT - SIM360 - CIS | CIS - TMS - PO Interface | Centralised Inbound Scheduling - Appointment Interface - Once TMS creates an Appointment pass that to SUS boxes. | 2023-09-15
ISCT | ISCT - OMNI | OMNI 1.0.0.4 | SUS to DOM Sales Order Creation, Supply & Order Event interface kinesis to kafka migration | 2023-09-06
ISCT | ISCT - SIM360 - PO | MERCH 1.5.0.45 | Apply Aurora I/O Optimized cluster mode to the production merchandising and integrated planning RDS clusters | 2023-09-06
ISCT | ISCT - SIM360 - PO | MERCH 1.5.0.47 | External link integration for SIM360 (CFM, FRDT and Imports App) | 2023-09-25
ISCT | ISCT - SIM360 - Door Dock Appoitment Scheduling | Dock Door Scheduling QA |  | 2024-02-16
ISCT | ISCT - SIM360 - CIS | CIS - TMS Fixes | Centralised Inbound Scheduling. Transport Management System | 2023-10-10
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release | Release 1.196.0v - VBT Commodity Flag | 2023-10-23
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.184.0v - PAT Refresh Anchor Point-Follower (LAP only) | 2023-09-06
Corp. Merchandising | CM - Apps Platform | VBT 2.1.0 |  | 2024-02-19
Corp. Merchandising | CM - PGI (Apps Team) | PGI 1.9.1 (Tentative) |  | 2024-02-22
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.167.0v - Blue Dot Revamp Rejection Logic (MVP 02) , Test Plan ¦ SDP -1.167.0v Release 1.175.0v - FnB "Deny" to "Rejected" , Test Plan ¦ SDP -1.175.0v Release 1.178.0v – PAT Override revised-pricing-lot with GAP Release 1.180.0v - Autoslotting - New Items Not getting pick up Release 1.181.0v - COO Banner | 2023-08-14
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release | Release 1.196.0v - VBT Commodity Flag ¦Test Plan ¦ VBT -1.196.0v | 2023-11-06
Corp. Merchandising | CM - Paper Lotting | Paper Lot CRs |  | 2023-12-01
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.8.1 |  | 2023-12-04
Corp. Merchandising | CM - Customer Decision Trees | CDT - 1.2.1 | Customer Decision Tress | 2023-12-04
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.8.0 | Big fixes and improvements | 2023-11-21
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.173.0v - Contact Management - PGI Role Enhancements | 2023-09-26
Corp. Merchandising | CM - IST Devolopment | IST 1.3.0 (Tentative) |  | 2024-02-12
Corp. Merchandising | ISCT - BAU/Engineering | Supplier Data Portal Release (Tentative) |  | 2024-02-05
Corp. Merchandising | CM - Customer Decision Trees | CDT - 1.2.0 | Customer Decision Trees | 2023-11-13
Corp. Merchandising | ISCT - Central Freight Management | Supplier Data Portal Minor Release | Release 1.141.0v - Item API JAVA 17 Update Release 1.174.0v - CN removal flag should pass to NetMenu directly (MVP 01) Release 1.204.0v - GAP Values not flowing down to LAP (Partially Released – SALES_LOAD schedule change only) | 2023-11-13
Corp. Merchandising | CM - IST Devolopment | IST 1.1.2 | Item Selection Tool | 2023-12-05
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Minor Release |  | 2023-11-20
Corp. Merchandising | CM - Customer Decision Trees | CDT 1.1.0 | Customer Decision Trees | 2023-09-26
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.189.0v - Fix multiple primary contacts | 2023-10-02
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.152.0v – Tech BAU Fargate Migration MVP 01 (Profiling API) | 2023-10-09
Corp. Merchandising | CM - Supplier Portal | Supplier Data Portal Release | Release 1.207.0v – F&B Auto Approval (Turn on AA Process) https://syscobt.atlassian.net/wiki/spaces/MDMSUPPLIER/pages/4131127488/Release+1.207.0v+-+F+B+Auto+Approval+Turn+on+AA+Process | 2024-01-08
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.9.0 (Tentative) |  | 2024-01-30
Corp. Merchandising | CM - PGI (Apps Team) | PGI DB Migration Prod Deployment |  | 2023-11-09
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.6.7 |  | 2023-07-31
Corp. Merchandising | CM - Supplier Portal | Supplier Portal Minor Release | Release 1.186.0v – PAT Global LPG Logic change (without report) ¦Test Plan ¦ PAT -1.186.0v Release 1.195.0v - Patch Feedback hide for non-supplier visible items No high/critical issues reported. | 2023-10-16
Corp. Merchandising | CM - IST Devolopment | IST 1.1.0 | Item Selection Tool | 2023-08-09
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.3 |  | 2023-09-26
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.0 |  | 2023-08-24
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.1 |  | 2023-09-06
Corp. Merchandising | CM - Supplier Fee | Supplier Fee 2.7.2 |  | 2023-09-12
Corp. Merchandising | CM - IST Devolopment | IST 1.1.1 | Item Selection Tool | 2023-10-03
OBT-Engineering | OBTE - Cortex | Cortex Pilot | East Texas (293) | 2023-07-29
OBT-Engineering | OBTE - Cortex | Cortex (08 OpCos) |  | 2023-11-04
OBT-Engineering | OBTE - Cortex | Cortex (2 OpCos) | 001-Jackson and 078-West Texas | 2023-08-26
OBT-Engineering | OBTE - Cortex | Cortex (3 OpCos) |  | 2023-09-09
OBT-Engineering | OBTE - Cortex | Cortex (10 OpCos) |  | 2023-11-11
OBT-Engineering | OBTE - BAU | Service Time Override (21 OpCos) |  | 2023-11-03
OBT-Engineering | OBTE - BAU | Service Time Override Changes | Delivery service time. Customer specific. Only updated customers will get updated to RoadNet | 2024-01-16
OBT-Engineering | OBTE - Cortex | Cortex (08OpCos) |  | 2024-01-13
OBT-Engineering | OBTE - Cortex | Cortex (14 OpCo) |  | 2024-01-27
OBT-Engineering | OBTE - Cortex | Cortex (3 OpCos) |  | 2023-10-01
OBT-Engineering | OBTE - ARI Modernization | ODI Changes to RN |  | 2023-09-22
OBT-Engineering | OBTE - Cortex | Cortex (6 OpCos) |  | 2023-10-08
OBT-Engineering | OBTE - Cortex | Cortex (09 OpCos) |  | 2023-10-21
OBT-Engineering | OBTE - Performance Culture | Stop Attribute MVP 1 (Tentative) |  | 2024-02-19
OBT-Engineering | OBTE - ARI Modernization | Pre Routing Go Live |  | 2023-08-07
OBT-Engineering | OBTE - BAU | Service Time Override (10 OpCos) | ODI service time send to Roadnet | 2023-10-21
OBT-Engineering | OBTE - Cortex | Cortex (09 OpCos) |  | 2023-10-28
OBT-Engineering |  | FY24 OMNI - April Release |  | 2024-04-27
OBT-Engineering | OBTE - ARI Modernization | Pre Routing Go Live |  | 2023-08-07
CDS | CDS - Enterprise Omni Channel | OMNI Dec 09 Release |  | 2023-12-09
CDS | CDS - Tech Initiatives | ASOH Streaming and Bulk Service |  | 2023-08-22
CDS | CDS - Enterprise Omni Channel | FY24 - OMNI Sep 29 Release | Bulk Order Subscription (BOS 2.0) | 2023-10-10
CDS | CDS - Enterprise Omni Channel | FY24 OMNI - June Release | Hub & Spoke | 2024-06-15
CDS | CDS - Enterprise Omni Channel | OMNI January Release |  | 2024-02-03
CDS | CDS - Enterprise Omni Channel | OMNI Oct 17th Releasse |  | 2023-10-20
CDS | CDS - Enterprise Omni Channel | OMNI 31st Oct Release | Bug fixes | 2023-11-11
CDS | CDS - Tech Initiatives | DR (Order Status Service) |  | 2024-01-28
GRAIN | GRAIN - GAH | GAH - Backend Revamp | Python 3.8 to 3.11 | 2024-04-30
GRAIN | GRAIN - Tableau (USBL) | Total Team Selling Dashboard Go-live |  | 2023-08-08
GRAIN | GRAIN - GAH | GAH - Frontend Revamp | Angular 5 to 17 | 2024-03-29
GRAIN | GRAIN - SOLAR | SOLAR - Onboarding Allan Town OpCo |  | 2024-04-30
GRAIN | GRAIN - Vision | Vision - Frontend Revamp |  | 2024-04-30
GRAIN | GRAIN - Tableau (USBL) | Tableau - Rebate Report Go-live |  | 2024-02-16
GRAIN | GRAIN - Tableau (USBL) | CX KPI Dashboard Go-live |  | 2023-08-25
GRAIN | GRAIN - Tableau (USBL) | Tableau - Event Chargeback Go-live |  | 2024-02-16
GRAIN | GRAIN - Tableau (USBL) | CX KPI Dashboard Go-live |  | 2024-01-11
GRAIN | GRAIN - Tableau (USBL) | US Ops Dashboard Go-live |  | 2023-09-27
GRAIN | GRAIN - Tableau (USBL) | Fuel Surcharge Dashboard Go-live |  | 2023-11-22
GRAIN | GRAIN - Tableau (USBL) | TTS Dashboard Go-live |  | 2023-10-13
GRAIN | GRAIN - Warehouse Live | WHL - Cache database integration |  | 2023-10-05
GRAIN | GRAIN - Tableau (USBL) | Total team Selling Dashboard Go-live |  | 2024-01-11
GRAIN | GRAIN - Warehouse Live | WHL - Onboarding RDC OpCos |  | 2024-02-16

## Releases
Team | Initiative | Bar Name | Start Date | End Date
SWMS | SWMS - Mobile Apps Modernization | SWMS Mobile Modernization | 2023-03-01 | 2024-03-31
SWMS | SWMS - Mobile Apps Modernization | Android 11 Migration | 2023-10-01 | 2024-03-01
SWMS | SWMS - Mobile Apps Modernization | HTTP to HTTPS Migration | 2023-03-01 | 2023-11-18
SWMS | SWMS - Mobile Apps Modernization | Ireland English | 2023-10-18 | 2023-11-17
SWMS | SWMS - Mobile Apps Modernization | MSKU | 2023-12-01 | 2024-01-31
SWMS | SWMS - Mobile Apps Modernization | R55 | 2023-04-03 | 2023-07-31
SWMS | SWMS - Mobile Apps Modernization | R56/R57 | 2023-12-01 | 2024-01-29
SWMS | SWMS - Mobile Apps Modernization | R58/59 | 2024-02-01 | 2024-03-31

## Field Data
Product/Initiative | Team
CDS - BAU | CDS
CDS - Enterprise Omni Channel | CDS
CDS - Tech Initiatives | CDS
CM - Apps Platform | Corp. Merchandising
CM - BAU/Engineering | Corp. Merchandising
CM - Customer Decision Trees | Corp. Merchandising
CM - IST Devolopment | Corp. Merchandising
CM - MDM Platform | Corp. Merchandising
CM - Paper Lotting | Corp. Merchandising
CM - PGI (Apps Team) | Corp. Merchandising
CM - PGM | Corp. Merchandising
CM - Supplier Fee | Corp. Merchandising
CM - Supplier Portal | Corp. Merchandising
GRAIN - Vision | GRAIN
GRAIN - SOLAR | GRAIN
GRAIN - GAH | GRAIN
GRAIN - Warehouse Live | GRAIN
GRAIN - Tableau (USBL) | GRAIN
GRAIN - ODI | GRAIN
OBTE - ARI Modernization | OBT-Engineering
OBTE - BAU | OBT-Engineering
OBTE - Cortex | OBT-Engineering
OBTE - Performance Culture | OBT-Engineering
SWMS - Blue Yonder (LMS) | SWMS
SWMS - Brakes | SWMS
SWMS - Chick-Fil-A | SWMS
SWMS - Cloud Acceleration | SWMS
SWMS - Cloud Agnostic | SWMS
SWMS - CMU Full Order Cross-Dock | SWMS
SWMS - Data Science | SWMS
SWMS - Delivery Sleeve | SWMS
SWMS - Enterprise Omni Channel | SWMS
SWMS - Infrastructure Upgrades (Oracle 19C) | SWMS
SWMS - Integrations Modernization | SWMS
SWMS - International | SWMS
SWMS - Mobile Apps Modernization | SWMS
SWMS - Modernization ProC to PL/SQL | SWMS
SWMS - OPCO | SWMS
SWMS - Platform | SWMS
SWMS - Platform DBA | SWMS
SWMS - Quinyx (LPS) | SWMS
SWMS - RDC | SWMS
SWMS - RDC Cloud Migration | SWMS
SWMS - Release Automation | SWMS
SWMS - SCM R&D | SWMS
SWMS - STS | SWMS
SWMS - SWAP | SWMS
SWMS - Test Automation & Stability | SWMS
SWMS - UI Modernization (New UI) | SWMS
SWMS - Warehouse Moves | SWMS
SWMS - Java Migration | SWMS
ISCT - BAU/Engineering | ISCT
ISCT - Central Freight Management | ISCT
ISCT - CFM/FRDT US Enhancements | ISCT
ISCT - DPR | ISCT
ISCT - DPR/SUS IMS & Merch Modernization | ISCT
ISCT - Global Inventory Management | ISCT
ISCT - Global Inventory Management (House Confirmation) | ISCT
ISCT - IA Enhancements | ISCT
ISCT - Imports App/SID | ISCT
ISCT - Integrated Planning | ISCT
ISCT - Item and Vendor API | ISCT
ISCT - Item Mainteance | ISCT
ISCT - OMNI | ISCT
ISCT - OMNI (IM Platform Dev & SUS to DOM Interface) | ISCT
ISCT - PO Management System | ISCT
ISCT - RME Platform Upgrade POC | ISCT
ISCT - SCM R&D | ISCT
ISCT - Service Level Insights | ISCT
ISCT - SIM360 - CIS | ISCT
ISCT - SIM360 - DFIO | ISCT
ISCT - SIM360 - Dock Door Appointment Scheduling | ISCT
ISCT - SIM360 - IA | ISCT
ISCT - SIM360 - Innovation | ISCT
ISCT - SIM360 - MSR Integration | ISCT
ISCT - SIM360 - Mule Modernization | ISCT
ISCT - SIM360 - PO | ISCT
ISCT - SIM360 - SLI | ISCT
ISCT - SIM360 - Vendor Cost Maintenance Modernization | ISCT
ISCT - SIM360 Vendor Confirmation | ISCT
ISCT - SIM360 - RDC Truckfill for SIM360 | ISCT
ISCT - SIM360 Pulse | ISCT